## Prouts details
Sr no | Segment | Chassis Number | DTC Code | DTC Name | DTC Status | Start Date | End Date | Age | Owner | Protus Number | Protus Stage | Model
1 | HD | MC2HCSRC0PE096303 | P20E892 | Reductant Pressure Too Low | Closed | 2024-11-07 | 2024-11-12 | 5 | Supal Solanki | VE2188_T-Endurance-C-0223 | Verification | Pro 6048T
2 | HD | MC2HCSRC0PE097377 | P202D7A | Reductant Leakage | Closed | 2024-11-07 | 2024-11-12 | 5 | Supal Solanki | VE2188_T-Endurance-C-0223 | Verification | Pro 6048T
3 | HD | MC2HCSRC0PD094477 | P11450 | Adblue Level is below 10% | Closed | 2024-11-07 | 2024-11-12 | 5 | Supal Solanki | VE2188_T-Endurance-C-0223 | Verification | Pro 6048T
4 | HD | MC2HCSRC0PD094476 | P202D7A | Reductant Leakage | Closed | 2024-11-07 | 2024-11-12 | 5 | Supal Solanki | VE2188_T-Endurance-C-0223 | Verification | Pro 6048T
5 | Titan | MC2JACRC0RDB00003 | P190512 | AUX Air Compressor current sensor fault | Open | 2024-11-20 |  | 19 | Chandan Kumar Parida | VE1430-BS VI seeding-C-0055 | Roadmap for DR/PM | Titan
6 | Titan | MC2JACRC0RDB00007 | P140116 | HVIL UnderVoltage | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0058 | Roadmap for DR/PM | Titan
7 | Titan | MC2JACRC0RDB00005 | P140116 | HVIL UnderVoltage | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0058 | Roadmap for DR/PM | Titan
8 | Titan | MC2JACRC0RDB00003 | P140116 | HVIL UnderVoltage | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0058 | Roadmap for DR/PM | Titan
9 | Titan | MC2JACRC0RDB00008 | P140116 | HVIL UnderVoltage | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0058 | Roadmap for DR/PM | Titan
10 | Titan | MC2JACRC0RDB00009 | P172313 | Low Side LS3 HVIL Relay Open Circuit | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0059 | Roadmap for DR/PM | Titan
11 | Titan | MC2JACRC0RDB00007 | P172313 | Low Side LS3 HVIL Relay Open Circuit | Open | 2024-11-20 |  | 19 | Ramakant Pandey | VE1430-BS VI seeding-C-0059 | Roadmap for DR/PM | Titan
12 | Titan | MC2JACRC0REB00009 | U1C019A | BCS CAN message timeout | Open | 2024-11-19 |  | 20 | Ramakant Pandey | VE1430-Endurance-C-0046 | Ramakant Pandey | Titan
13 | Titan | MC2JACRC0RDB00008 | U1C019A | BCS CAN message timeout | Open | 2024-11-19 |  | 20 | Ramakant Pandey | VE1430-Endurance-C-0046 | Ramakant Pandey | Titan
14 | HD | MC2HCSRC0PB090273 | P107C14 | Range inhibitor valve malfuctioning | Open | 2024-11-27 |  | 12 | Hemant Jewalkar | VE2188_T-Endurance-P-0075 | Roadmap for DR/PM | Pro 6048T
15 | HD | MC2HCSRC0PB090274 | P107C14 | Range inhibitor valve malfuctioning | Open | 2024-11-27 |  | 12 | Hemant Jewalkar | VE2188_T-Endurance-P-0075 | Roadmap for DR/PM | Pro 6048T
16 | HD | MC2HCSRC0PD094477 | P107C14 | Range inhibitor valve malfuctioning | Open | 2024-11-27 |  | 12 | Hemant Jewalkar | VE2188_T-Endurance-P-0075 | Roadmap for DR/PM | Pro 6048T
17 | HD | MC2HCSRC0PE096303 | P107C14 | Range inhibitor valve malfuctioning | Open | 2024-11-27 |  | 12 | Hemant Jewalkar | VE2188_T-Endurance-P-0075 | Roadmap for DR/PM | Pro 6048T
18 | HD | MC2HCSRC0PB090273 | P02190 | Engine RPM exceeds threshold 3900RPM. | Open | 2024-11-27 |  | 12 | Hemant Jewalkar | VE2188_T-Endurance-P-0075 | Roadmap for DR/PM | Pro 6048T
19 | HD | MC2HCSRC0PE096305 | P048013 | E-Viscous FANs actuator signal Open Circuit | Closed | 2024-11-28 | 2024-12-02 | 4 | Ashish Kumar Paroha | VE2188_T-Endurance-P-0076 | Verification | Pro 6048T
20 | HD | MC2HCSRC0PB090278 | P048013 | E-Viscous FANs actuator signal Open Circuit | Closed | 2024-11-28 | 2024-12-02 | 4 | Ashish Kumar Paroha | VE2188_T-Endurance-P-0076 | Verification | Pro 6048T
21 | HD | MC2HCSRC0PD094476 | P020112 | Bank 1 of Injector Short Circuit to High or Battery | Closed | 2024-11-28 | 2024-12-06 | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0229 | Roadmap for DR/PM | Pro 6048T
22 | HD | MC2HCSRC0PD094476 | P020212 | Bank 2 of Injector Short Circuit to High or Battery | Closed | 2024-11-28 | 2024-12-06 | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0229 | Roadmap for DR/PM | Pro 6048T
23 | HD | MC2HCSRC0PD094476 | P020312 | Bank 3 of Injector Short Circuit to High or Battery | Closed | 2024-11-28 | 2024-12-06 | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0229 | Roadmap for DR/PM | Pro 6048T
24 | HD | MC2HCSRC0PE0969605 | P040397 | EGR Control Component or System Operation failure | Open | 2024-11-28 |  | 11 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0228 | Roadmap for DR/PM | Pro 6048T
25 | HD | MC2HCSRC0PE0969605 | P040313 | EGR Control Open Circuit | Open | 2024-11-28 |  | 11 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0228 | Roadmap for DR/PM | Pro 6048T
26 | HD | MC2HCSRC0PE0969605 | P228F00 | Open load error for EGRVlv H-Bridge powerstage | Open | 2024-11-28 |  | 11 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0228 | Roadmap for DR/PM | Pro 6048T
27 | HD | MC2DALRC0PC005349 | P245213 | Particulate Filter Pressure Sensor Open Ciruit | Open | 2024-12-01 |  | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-BS VI seeding-C-0046 | Roadmap for DR/PM | Pro 8035XM
28 | HD | MC2DALRC0PC005349 | P10E10 | Affertreatment 1 Diesel Particulate Filter Differential Pressure Data Valid But Above Normal | Open | 2024-12-01 |  | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-BS VI seeding-C-0046 | Roadmap for DR/PM | Pro 8035XM
29 | HD | MC2HCSRC0PE097378 | P204F93 | Reductant Return No Flow Detected | Open | 2024-12-01 |  | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0230 | Roadmap for DR/PM | Pro 6048T
30 | HD | MC2HCSRC0PE097378 | P10CE97 | Reductant System Performance Bank 1 error | Open | 2024-12-01 |  | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0230 | Roadmap for DR/PM | Pro 6048T
31 | HD | MC2HCSRC0PE096304 | P204F93 | Reductant System Performance Bank 1 | Open | 2024-12-01 |  | 8 | Hardik Narendrabhai Lakhlani | VE2188_T-Endurance-C-0230 | Roadmap for DR/PM