## Sheet1
Segment/section | Str no. | DTC | Protus Name | Status (O/C) | start data and time | End date and time | Owner | Status | Description | Ageing | Status
HD | MC2HCSRC0PE096303 | P20E892 | VE2188_T-Endurance-C-0223 | C | 2024-11-07 | 2024-11-12 | Supal Solanki | Validation Closed | Reductant Pressure Too Low | 5 | Closed
HD | MC2HCSRC0PE097377 | P202D7A | VE2188_T-Endurance-C-0223 | C | 2024-11-07 | 2024-11-12 | Supal Solanki | Validation Closed | Reductant Leakage | 5 | Closed
HD | MC2HCSRC0PD094477 | P11450 | VE2188_T-Endurance-C-0223 | C | 2024-11-07 | 2024-11-12 | Supal Solanki | Verification | Adblue Level is below 10% | 5 | Closed
HD | MC2HCSRC0PD094476 | P202D7A | VE2188_T-Endurance-C-0223 | C | 2024-11-07 | 2024-11-12 | Supal Solanki | Verification | Reductant Leakage | 5 | Closed
HD | MC2HCSRC0PE096305 | P048013 | VE2188_T-Endurance-P-0076 | C | 2024-11-28 | 2024-12-02 | Ashish Kumar Paroha |  | E-Viscous FANs actuator signal Open Circuit | 4 | Closed
HD | MC2HCSRC0PB090278 | P048013 | VE2188_T-Endurance-P-0076 | C | 2024-11-28 | 2024-12-02 | Ashish Kumar Paroha |  | E-Viscous FANs actuator signal Open Circuit | 4 | Closed
HD | MC2HCSRC0PD094476 | P020112 | VE2188_T-Endurance-C-0229 | C | 2024-11-28 | 2024-12-06 | Hardik Narendrabhai Lakhlani |  | Bank 1 of Injector Short Circuit to High or Battery | 8 | Closed
HD | MC2HCSRC0PD094476 | P020212 | VE2188_T-Endurance-C-0229 | C | 2024-11-28 | 2024-12-06 | Hardik Narendrabhai Lakhlani |  | Bank 2 of Injector Short Circuit to High or Battery | 8 | Closed
HD | MC2HCSRC0PD094476 | P020312 | VE2188_T-Endurance-C-0229 | C | 2024-11-28 | 2024-12-06 | Hardik Narendrabhai Lakhlani |  | Bank 3 of Injector Short Circuit to High or Battery | 8 | Closed
EV | MC2JACRC0RDB00009 | P172313 | VE1430-BS VI seeding-C-0059 | P | 2024-11-20 |  | Ramakant Pandey | Part Avaibility | Low Side LS3 HVIL Relay Open Circuit | 19 | WIP
EV | MC2JACRC0RDB00007 | P172313 | VE1430-BS VI seeding-C-0059 | P | 2024-11-20 |  | Ramakant Pandey | Validation Closed | Low Side LS3 HVIL Relay Open Circuit | 19 | WIP
EV | MC2JACRC0REB00009 | U1C019A | VE1430-Endurance-C-0046 | P | 2024-11-19 |  | Ramakant Pandey | Verification | BCS CAN message timeout | 20 | WIP
EV | MC2JACRC0RDB00008 | U1C019A | VE1430-Endurance-C-0046 | P | 2024-11-19 |  | Ramakant Pandey | ECO Implementation | BCS CAN message timeout | 20 | WIP
HD | MC2HCSRC0PB090273 | P107C14 | VE2188_T-Endurance-P-0075 | P | 2024-11-27 |  | Hemant Jewalkar | Validation Closed | Range inhibitor valve malfuctioning | 12 | WIP
HD | MC2HCSRC0PB090274 | P107C14 | VE2188_T-Endurance-P-0075 | P | 2024-11-27 |  | Hemant Jewalkar |  | Range inhibitor valve malfuctioning | 12 | WIP
HD | MC2HCSRC0PD094477 | P107C14 | VE2188_T-Endurance-P-0075 | P | 2024-11-27 |  | Hemant Jewalkar |  | Range inhibitor valve malfuctioning | 12 | WIP
HD | MC2HCSRC0PE096303 | P107C14 | VE2188_T-Endurance-P-0075 | P | 2024-11-27 |  | Hemant Jewalkar |  | Range inhibitor valve malfuctioning | 12 | WIP
HD | MC2HCSRC0PB090273 | P02190 | VE2188_T-Endurance-P-0075 | P | 2024-11-27 |  | Hemant Jewalkar |  | Engine RPM exceeds threshold 3900RPM. | 12 | WIP
EV | MC2JACRC0RDB00003 | P190512 | VE1430-BS VI seeding-C-0055 | P | 2024-11-20 |  | Chandan Kumar Parida | Verification | AUX Air Compressor current sensor fault | 19 | WIP
EV | MC2JACRC0RDB00007 | P140116 | VE1430-BS VI seeding-C-0058 | P | 2024-11-20 |  | Ramakant Pandey | Roadmap for DR/PM | HVIL UnderVoltage | 19 | WIP
EV | MC2JACRC0RDB00005 | P140116 | VE1430-BS VI seeding-C-0058 | P | 2024-11-20 |  | Ramakant Pandey | Closure | HVIL UnderVoltage | 19 | WIP
EV | MC2JACRC0RDB00003 | P140116 | VE1430-BS VI seeding-C-0058 | P | 2024-11-20 |  | Ramakant Pandey | Validation Closed | HVIL UnderVoltage | 19 | WIP
EV | MC2JACRC0RDB00008 | P140116 | VE1430-BS VI seeding-C-0058 | P | 2024-11-20 |  | Ramakant Pandey | Verification | HVIL UnderVoltage | 19 | WIP
HD | MC2HCSRC0PE0969605 | P040397 | VE2188_T-Endurance-C-0228 | P | 2024-11-28 |  | Hardik Narendrabhai Lakhlani |  | EGR Control Component or System Operation failure | 11 | WIP
HD | MC2HCSRC0PE0969605 | P040313 | VE2188_T-Endurance-C-0228 | P | 2024-11-28 |  | Hardik Narendrabhai Lakhlani |  | EGR Control Open Circuit | 11 | WIP
HD | MC2HCSRC0PE0969605 | P228F00 | VE2188_T-Endurance-C-0228 | P | 2024-11-28 |  | Hardik Narendrabhai Lakhlani |  | Open load error for EGRVlv H-Bridge powerstage | 11 | WIP
LMD | MC2DALRC0PC005349 | P245213 | VE2188_T-BS VI seeding-C-0046 | P | 2024-12-01 |  | Hardik Narendrabhai Lakhlani |  | Particulate Filter Pressure Sensor Open Ciruit | 8 | WIP
LMD | MC2DALRC0PC005349 | P10E10 | VE2188_T-BS VI seeding-C-0046 | P | 2024-12-01 |  | Hardik Narendrabhai Lakhlani |  | Affertreatment 1 Diesel Particulate Filter Differential Pressure Data Valid But Above Normal | 8 | WIP
BUS | MC2HCSRC0PE097378 | P204F93 | VE2188_T-Endurance-C-0230 | P | 2024-12-01 |  | Hardik Narendrabhai Lakhlani |  | Reductant Return No Flow Detected | 8 | WIP
BUS | MC2HCSRC0PE097378 | P10CE97 | VE2188_T-Endurance-C-0230 | P | 2024-12-01 |  | Hardik Narendrabhai Lakhlani |  | Reductant System Performance Bank 1 error | 8 | WIP
BUS | MC2HCSRC0PE096304 | P204F93 | VE2188_T-Endurance-C-0230 | P | 2024-12-01 |  | Hardik Narendrabhai Lakhlani |  | Reductant System Performance Bank 1 | 8 | WIP